## Sheet1
Project and Task Planning
Customer: | Mr/Waled
Project: | Digital Air Conditioning Screen
Date: | March 5th, 2016
Author: | Ahmed Elmenshawy
Phases and Tasks
Initiation | Min | Avg. | Max | Expected | Project Role
under stand lcd and deal with it | 0.5 | 0.5 | 2 | 0.75 | PM
how to control fan of air condition | 0.5 | 0.5 | 2 | 1 | PM
what is suitable , max and min temperature | 0.25 | 0.25 | 1 | 0.29167 | PM
deal with different swithes and control it | 0.25 | 0.25 | 2 | 0.29167 | PM
Sum of Initiation Activities | 1.6 | 1.6 | 7 | 2.3333
Definition | Min | Avg. | Max | Expected
Requirement Specification Gathering | 1 | 1 | 3 | 1.3333 | Consultant
Test Plan | 1 | 1 | 3 | 1.3333 | PM
Requirements Sign-off Meeting | 0.25 | 0.25 | 0.25 | 0.25 | PM
Project Plan Update | 0.25 | 0.25 | 0.25 | 0.25 | PM
Sum of Definition Activities | 2.5 | 2.5 | 6.5 | 3.1667
Testing | Min | Avg. | Max | Expected
Test Support and Test Approval | 5 | 7 | 15 | 8 | Consultant
Follow up and re-work | 2 | 3 | 5 | 3.1667 | Consultant
UAT Support | 1 | 1 | 2 | 1.1667 | Consultant
Sum of Testing Activities | 8 | 11 | 22 | 12.3333
Go Live | Min | Avg. | Max | Expected
Final and complete documentation |  | 16 | 4 | 11.3333 | Consultant
Customer knowledge transfer and education |  |  |  | 0 | Consultant
Delivery to live environment |  |  |  | 0 | Consultant
Project Sign Off Meeting | 0.25 | 0.25 | 0.25 | 0.25 | PM
Sum of Go Live Activities | 0.25 | 0.25 | 0.25 | 11.5833