## Sheet1
Project Name: | Digital Air Conditioning Screen
Project Manager: | Hadeer Rashid
Review No | Periority | Document Name | Comment | Assigned Person | Start time | End time | Status | Reviewer
Rev_00_01 | High | Estimation Sheet | Adapt Time w.r.t plan schedual | Menshawy | 2016-12-03 | 13/3/2016 | DONE | Hossam
Rev_00_02 | Meduim | Estimation Sheet | Calculate Total Time | Menshawy | 2016-12-03 | 13/3/2016 | DONE | Hossam
Rev_01_01 | Meduim | Risk Sheet | Add if File Lost situation | Belal | 2016-12-03 | 2016-12-03 | DONE | Hossam
Rev_02_01 | Meduim | CI list | Add all folders(Test,…..) | Hossam | 2016-12-03 | 14/3/2016 | DONE | Hossam
Rev_02_02 | High | CI list | Update GitHub folders | Hossam | 2016-12-03 | 17/3/2016 | DONE | Hossam
Rev_03_01 | Meduim | CRS | Make Device portable | Fatma | 2016-12-03 | 14/3/2016 | DONE | Hossam
Rev_03_02 | High | CRS | Set minimum size of LCD | Fatma | 2016-12-03 | 14/3/2016 | DONE | Hossam
Rev_02_03 | Low | CI list | Add Code folders | Hossam | 2016-02-04 | 2016-03-04 | DONE | Hossam