## Sheet1
Project Name: | Digital Air Conditioning Screen
Project Manager: | Hadeer Rashid
Review No | Periority | Document Name | Comment | Assigned Person | Start time | End time | Status | Reviewer
Rev_00_01 | High | Estimation Sheet | Adapt Time w.r.t plan schedual | Menshawy | 2016-12-03 | 13/3/2016 | DONE | Hossam
Rev_00_02 | Meduim | Estimation Sheet | Calculate Total Time | Menshawy | 2016-12-03 | 13/3/2016 | DONE | Hossam
Rev_01_01 | Meduim | Risk Sheet | Add if File Lost situation | Belal | 2016-12-03 | 2016-12-03 | DONE | Hossam
Rev_02_01 | Meduim | CI list | Add all folders(Test,…..) | Hossam | 2016-12-03 | 14/3/2016 | DONE | Hossam
Rev_02_02 | High | CI list | Update GitHub folders | Hossam | 2016-12-03 | 17/3/2016 | DONE | Hossam
Rev_03_01 | Meduim | CRS | Make Device portable | Fatma | 2016-12-03 | 14/3/2016 | DONE | Hossam
Rev_03_02 | High | CRS | Set minimum size of LCD | Fatma | 2016-12-03 | 14/3/2016 | DONE | Hossam
Rev_02_03 | Low | CI list | Add Code folders | Hossam | 2016-02-04 | 2016-03-04 | DONE | Hossam
Rev_03_03 | High | CRS | Add more information about project | Fatma | 2016-02-04 | 2016-03-04 | DONE | Hossam
Rev_04_01 | High | SRS | Add new requirement | Menshawy | 2016-03-04 | 2016-04-04 | DONE | Hossam
Rev_05_01 | Meduim | SIQ | Add quistion about rang of Speed &Temp | Fatma | 2016-03-04 | 2016-04-04 | DONE | Hossam
Rev_06_01 | Meduim | HLD | Add interactive between Layers | Belal | 2016-05-04 | 2016-06-04 | DONE | Hossam
Rev_07_01 | Meduim | CDD LCD | Add Tags | Menshawy | 2016-06-04 | 2016-07-04 | DONE | Hossam
Rev_08_01 | Meduim | CDD DIO | Add Tags | Belal | 2016-06-04 | 2016-07-04 | DONE | Hossam
Rev_09_01 | Meduim | CDD EEPROM | Add Tags | Fatma | 2016-06-04 | 2016-07-04 | DONE | Hossam
Rev_10_01 | Meduim | CDD TS | Add Tags | Hadir | 2016-06-04 | 2016-07-04 | DONE | Hossam
Rev_11_01 | Meduim | Test Cases | Add new Test Cases with tags | Fatma | 2016-06-04 | 2016-07-04 | DONE | Hossam
Rev_12_01 | High | RTM | Make connection between Tags | Hadir | 2016-07-04 | 2016-08-04 | DONE | Hossam
Rev_13_01 | High | Code | Make Max & Min Temp and Speed Configurable by the user | Hossam | 2016-06-04 | 2016-08-04 | DONE | Hossam